## Sheet1
| TASK DELIVERY FORM | [8 empty] | TASKS
| Group Members | T1 | T2 | T3 | T4 | T5 | T6 | T7 | T8 | T9 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24
Rob | bar: T1; T4; TASKS T9; TASKS T13 to TASKS T20; TASKS T22
George | bar: T1; T4; T8 to TASKS T9; TASKS T12 to TASKS T13; TASKS T17; TASKS T21 to TASKS T24
Micah | bar: T1; T3; T5 to T8; TASKS T10 to TASKS T12; TASKS T14 to TASKS T16; TASKS T18 to TASKS T20
Rodrigo | bar: T1 to T2; T6 to T8; TASKS T10 to TASKS T12; TASKS T14 to TASKS T16; TASKS T18 to TASKS T20
James | bar: T1; T4; T8 to TASKS T9; TASKS T13; TASKS T17; TASKS T21 to TASKS T23
| Status of Compeltetion | 100% | 75% (needs revision) | 100% | 100% | 95% | 60% | 90% | 60% | 50% | 60% | 90% | 60% | 50% | 60% | 90% | 60% | 50% | 60% | 90% | 50% | 50% | 100% | 100% | 100%
List of Tasks |  | TASKS T9: Signatures
T1 | Initial setup (source control, Kanban, Gantt) | TASKS T9: Robert
T2 | Class Diagrams | TASKS T9: George
T3 | Database Diagrams | TASKS T9: Micah
T4 | Use Case Diagrams | TASKS T9: Rodrigo
T5 | Database Development | TASKS T9: James
T6 | Login Model
T7 | Login Controller
T8 | Login View
T9 | Login Test Cases
T10 | Patient Model
T11 | Patient Controller
T12 | Patient View
T13 | Patient Test Cases
T14 | Staff Model
T15 | Staff Controller
T16 | Staff View
T17 | Staff Test Cases
T18 | Admin Model
T19 | Admin Controller
T20 | Admin View
T21 | Admin Test Cases
T22 | Systems Diagrams
T23 | Sequence Diagrams
T24 | Website Wireframes